## Sheet1
|  | Project Name: | TDL - To Do List Application
|  | Project Description: | Application to manage a ToDoList using Front and Back end technologies
|  | Project Owner: | Waleed Tahir
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 18.1.21 | covid-19 | Potential for me or someone in my immediate proximity to contract the virus and cause me to be both unwell and in a state of lockdown |  |  | x |  | x |  | Impact on my workrate as a result of being ill or having to take care of someone who is ill | Ongoing | Wash hands and hand santise regularily as well as follwing the latest government guidlines to minimize the potential risk of encountering teh virus in teh first place.
2 | 18.1.21 | Damage to laptop | Potential of my laptop to be damaged either physically from something liek a drop or from a software perscective | x |  |  |  |  | x | would leave me unable to continue working until a replacement could be sorted | 1 week | Maintain good practice in teh upkeeo and storage of my laptop as well as ensuring a clean working environment e.g. no nearby drinks
3 | 27/1/21 | Lack of technocal knowledge | New to coding and so I have limited experfience working with language logic and more complex coding problems. | x |  |  |  | x |  | Will inevitably slow my progress down putting more pressure on the completion time of the project | Ongoing | Rely on the resources provided to me as well as consolidating my learning as I progress.
4 | 2021-05-02 | Schedule managment | Exceeding the neccesary time constraints |  | x |  |  | x |  | will mean that I do not have a complete build on the day of my presentation | ongoing | Manage time effectivly using supporting tools such as Jira board
5 | 2021-05-02 | Stress and Fatigue | Over working in an attemt to exceed the scope or offset time pressure | x |  |  |  | x |  | Will lead to a decrease in quality due to not being able to produce my highest quality of work | ongoing | Take regular breaks from screen and from work to allow myself to reset and adjust my condition
6 | 2021-05-02 | Scope creep | Veering outside of the MVP deliverables due to misdirection |  | x |  |  | x |  | Will waste time and reduce the completion of teh project in regards to the core MVP deliverables | ongoing | Stick to the key MVP deliverables to ensure the client receives the product requested
7 | 2021-07-02 | Connectivity Issues | As the front end of the application is reelient on being hosted my local host a stable internet connection is required to develop the front end | x |  |  |  |  | x | will slwo down the development process due to time lost as a result of loss of connectivity | ongoing | Manage Bandwith usage as much as possible to minimise slowing down or dropping of connection
8 | 2021-09-02 | Productivity issues | Delays in working or loss of work hours will further increase the remaining burden on the project | x |  |  |  | x |  | will lead to a decrease in effecieny and increase the likelyhood of scope not being met | ongoing | Manage Time responsible and stick to schedule to esnure project stays on track
9
10